## Product Backlog
Product Backlog
Priority | Story or Feature | Estimate in Points | Acceptance Criteria | Definition of DONE
1 | As a smartphone user, I want to be able to make and recieve phone calls, so I can communicate with others | 4 | The smartphone should have a contacts app. The smartphone should be able to make an outgoing call. The smartphone should be able to recieve an incoming call The smartphone should have a speaker and microphone. | User should be able to store contacts and retrieve/edit that information later User should be able to use their sim card to connect to cellular services User should be able to dial numbers or use contact app to make calls to other phones
2 | As a smartphone user, I want to be able to use wired accessories, so that I can use chargers, headphones, and other components that require a physical connection | 3 | The smartphone should have a variety of ports and connectors to support a wide range of wired accessories, such as headphones, chargers, and USB drives. The smartphone should be able to detect when a wired accessory is connected, and adjust its settings and behaviour accordingly. | Device should have software regulating power draw to ensure universal compatibility with chargers Device should detect if something is connected to audio port, thus switching audio from speakers to AUX output Device should recognize non-powered peripherals and interface with them as expected (i.e using USB to read data, using HDMI adapter to output video)
3 | As a smartphone user, I want to be able to send/recieve text messages to communicate on my own time. | 3 | smartphone should have a text messages app smartphone should be able to send/recieve text messages smartphone should be able to send/recieve voice messages | User should be able to send SMS texts to either other phone numbers, or to contacts stored on phone User should be able to receive SMS texts that will get sorted based on contact/phone number User should also be able to use cellular data to send/receive voice/video/picture files supported through SMS protocol
4 | As a user, I want to be able to use the internet through both Wi-Fi and cellular data to accomplish tasks such as send emails, conduct research, etc. | 4 | The smartphone should have a Wi-Fi settings page. The Wi-Fi settings page should display available Wi-Fi networks. The smartphone should be able to connect to Wi-Fi networks. The smartphone should be able to connect to cellular data to use the internet. | Phone should be able to connect to WiFi networks and be able to store connection details Phone should be able to recognize familiar networks and auto-connect when available Phone should prioritize WiFi connections but also be able to switch to data when network connectivity is down User should be able to manually change/erase/update connection settings through settings app
5 | As a user I want to make sure there is user authentication so that my personal information is secure. | 2 | User can create an account to log into device Smartphone can save user passcode Smartphone can use face-identification to access phone Smartphone locks when there are more than 5 failed attemps | User should be prompted to create or sign into account upon initial setup User should be prompted to use their chosen form of authentication each time phone wakes from sleep/rest mode Device should have built in anti-theft security measueres such as device lock-out and location tracking in event of multiple consecutive failed authentication attempts
6 | As a user, I want to be able to use the camera to campture moments in photo or video form. | 3 | The camera application can take high-resolution photos/videos All media is saved in the “Photos” folder Camera can zoom in/out when in use Media can be shared and saved between contacts Applications can access photos and videos on user's smartphone | User should be able to take pictures with the ease of a point and click camera Pictures should be stored in a photos album and sorted by date Other applications can access the photos on storage
7 | As a user, I want to access settings to customize the smartphone's main features such as the display and ringtone. | 5 | smartphone should be able to adjust the display of the screen smartphone should be able to optimize battery life smartphone should be able to change the ringtone smartphone should be able to access bluetooth feature smartphone should be able to set up user account | Basic functionality such as volume, brightness, airplane mode, etc should be accesible from a quick menu Other customization features such as wallpaper and ringtones should be accesible through settings application
8 | As a user, I want to be able to access and use bluetooth features to connect with my car, headphones, speakers, etc. | 1 | Smartphone can detect and connect to bluetooth devices Smartphone can save devices to connect to in the future Smartphone should be able to navigate through the connected device's controls (ex. volume) | User should be able to intuitively connect to bluetooth devices through settings Device should reconnect to previously paired devices when in range Devices should work as expected
9 | As a user, I want to be able to listen to music, so that I don't need to use an iPod to play my songs and make playlists. | 3 | The user should be able to create playlists The user should be able to save songs to their device The application should provide options to shuffle, play, or repeat songs. The application should be able to organize music based on artists, song titles, albums, and genres. | User should have access to a music application that allows them to playback music files App should allow user to sort music into playlists, or sort by other identifying metadata such as artist, album, year, etc
10 | As a user, I want to be able to download applications to access social media, lifestyle, education, navigation, entertainment apps, and more. | 5 | Smartphone is able to access and download applications from a central app store | User should have access to an application storefront to download 3rd party applications
11 | As a user, I want to ensure my phone is durable so that I can use it for a long period. | 2 | Phone screen is durable enough to resist cracks and scratches Phone should be water resistant | Durability tests should be completed prior to release of phone to ensure it withstands average use case situations such as drops, scrapes, and water exposure
12 | As a user, I want to be able to able to use a GPS application, so I can get directions to find my way to destinations. | 3 | The GPS app should be easy to use and provide clear directions. The app should be able to calculate and display multiple routes. The GPS should be able to provide information on real-time traffic and give suggestions for the fastest routes. The app should be able to provide voice-guided directions. | User should be able to use phones cellular connectivity to locate themselves on a map application User should be able to find directions to other locations from their current location, optimizing for things such as traffic, distance, and tolls
13 | As a user, I want to use voice assistant to operate the smartphone with voice commands. | 5 | The voice assistant should be able to recognize and respond to a wide range of requests. The voice assistant should be able to provide accurate and helpful responses to users' requests. The voice assistant should be able to perform a variety of tasks and actions, such as setting reminders, sending messages, making calls, and playing music. | User should be able to use intuitive voice commands to control basic functionality of phone An API should be provided so third-party developers can also create their own voice commands to control their own apps
14 | As a user, I want to access mobile payment apps, so that I can make purchases and transactions without a physical card. | 1 | The payment app should be secure and protect the user's financial information. The app should work with popular payment methods and banks. Adding forms of payment like credit or debit cards should be easy to set up. The app should provide receipts and transaction histories for each payment. | User should be able to use NFC technology on phone to complete payments Phone should save payment information to use either through NFC or for online payments, and lock the use of those payments behind verification such as face, passcode, or fingerprint
Note on C2: Students list MRF

## Sprint 1 Backlog
| Sprint 1 Goal | Enter the goal of your Sprint 1: To complete highest priority features so that basic smartphone functionalities are met.
Enter your TOTAL team capacity in real minutes:
Select the highest priority Features or Stories for your Sprint | Sprint 1 Backlog |  | Estimate each task in real time
| Story or Feature | Tasks | Estimate in Real Minutes | Resource Name
| Enter user story here: As a smartphone user, I want to be able to make and recieve phone calls, so I can communicate with others | Task 1: Implement a dialer app to initiate and receive calls. | 1200 | Lina Dbagh
|  | Task 2: Develop a call management system to handle incoming and outgoing calls. | 1500 | Mansi Mistry
|  | Task 3: Integrate the phone app with the smartphone's microphone and speaker system to ensure proper audio input and output. | 1000 | Puneet Shokar
|  | Task 4: Test the call feature to ensure good performance and reliability. | 900 | Usman Khan
|  | Total | 4600
| Enter another feature: As a smartphone user, I want to be able to use wired accessories, so that I can use chargers, headphones, and other components that require a physical connection | Task 1: Design and implement port(s) to connect wired accessories to the device. | 1600 | Lina Dbagh
|  | Task 2: Integrate the port(s) with the software to support the accessories' functionality on the smartphone. | 1200 | Mansi Mistry
|  | Task 3: Test the port's compatibility and functionality with different wired accessories, including chargers, headphones, etc. | 1000 | Puneet Shokar
|  | Task 4: Enable error warnings when a user inputs an incompatible accessory to the device. | 900 | Usman Khan
|  | Total | 4700
| Enter another feature: As a smartphone user, I want to be able to send/recieve text messages to communicate on my own time. | Task 1: Add a messages feature to send and receive messages within an inbox | 1200 | Lina Dbagh
|  | Task 2: Develop contact management to keep a log of contacts a user can message | 1500 | Mansi Mistry
|  | Task 3: Allow messages to send multimedia including photos and videos | 900 | Puneet Shokar
|  | Task 4: Integrate notification option so user gets notified for unread messages | 600 | Usman Khan
|  | Total | 4200
| Enter another feature: As a user, I want to be able to use the internet through both Wi-Fi and cellular data to accomplish tasks such as send emails, conduct research, etc. | Task 1: Enable network connectivity to connect to wifi or cellular data | 900 | Lina Dbagh
|  | Task 2: Test the authentication systems to ensure the network is secure and safe to use | 1000 | Mansi Mistry
|  | Task 3: Test that connection is reliable and strong enough to use for all applications | 300 | Puneet Shokar
|  | Task 4: Develop a feature to track internet usage incase of limited access | 240 | Usman Khan
|  | Total | 2440
| Enter another feature: As a user I want to make sure there is user authentication so that my personal information is secure. | Task 1: Develop a user authentication system to ensure secure access to the device through either touch ID or face ID. | 1700 | Lina Dbagh
|  | Task 2: Implement secure storage and encryption mechanisms to protect user data such as passwords. | 1300 | Mansi Mistry
|  | Task 3: Test the authentication and security mechanisms to ensure proper functionality and reliability. | 1000 | Puneet Shokar
|  | Task 4: Integrate the authentication system with different apps and services so users can log into applications using either their passcode, face ID, or touch ID. | 1200 | Usman Khan
|  | Total | 5200
| Enter another feature: As a user, I want to be able to use the camera to capture moments in photo or video form. | Task 1: Design and implement a phone camera to capture photos and videos. | 2100 | Lina Dbagh
|  | Task 2: Develop a camera app to enable camera functionality. | 1700 | Mansi Mistry
|  | Task 3: Develop storage medium to store and manage photos and videos. | 1200 | Puneet Shokar
|  | Task 4: Test the camera and camera app's functionality to ensure proper photo and video capture. | 800 | Usman Khan
|  | Total | 5800
| Enter another feature: As a user, I want to access settings to customize the smartphone's main features such as the display and ringtone. | Task 1: Develop a settings application to control the smartphone's main features such as user account | 2100 | Lina Dbagh
|  | Task 2: Develop access to change the smartphone's display settings (brightness, wallpaper, etc) | 1000 | Mansi Mistry
|  | Task 3: Add a feature to optimize battery life | 900 | Puneet Shokar
|  | Task 4: Develop feature to customize notification settings such as ringtone, vibration, or silent | 1300 | Usman Khan
|  | Total | 5300
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0

## Sprint 2 Backlog
| Sprint 2 Goal | Enter the goal of your Sprint 2
Enter your TOTAL team capacity in real minutes:
Select the highest priority Features or Stories for your Sprint | Sprint 2 Backlog |  | Estimate each task in real time
| Story or Feature | Tasks | Estimate in Real Minutes | Resource Name
| As a user, I want to be able to access and use bluetooth features to connect with my car, headphones, speakers, etc. | Task 1 Create API that handles things such as volume control and sound input/output based on universal standards | 1800 | Lina Dbagh
|  | Task 2 Create driver for bluetooth antenna to interface with device | 1400 | Mansi Mistry
|  | Task 3 Create software for managing bluetooth connections in settings | 1650 | Puneet Shokar
|  | Task 4 Create software logic for managing bluetooth connections (i.e autoconnecting, disconnecting when out of range, etc) | 1200 | Usman Khan
|  | Total | 6050
| As a user, I want to be able to listen to music, so that I don't need to use an iPod to play my songs and make playlists. | Task 1 Create an application that allows for downloading of music | 1400 | Lina Dbagh
|  | Task 2 Create a feature that allows users to save songs to a playlist | 1750 | Mansi Mistry
|  | Task 3 Create a feature that provides options to shuffle, play, or repeat songs. | 1200 | Puneet Shokar
|  | Task 4 Build the application in a way that its able to organize music based on artists, song titles, albums, and genres | 2000 | Usman Khan
|  | Total | 6350
| As a user, I want to be able to download applications to access social media, lifestyle, education, navigation, entertainment apps, and more. | Task 1 Create developer tools to allow 3rd party companies to develop applications for our platform | 2000 | Lina Dbagh
|  | Task 2 Setup developer portal to submit applications to be put on store | 1200 | Mansi Mistry
|  | Task 3 Create storefront application that allows users to download applications | 1600 | Puneet Shokar
|  | Task 4 Connect storefront with backend servers to provide authentication for payment and host downloads | 1400 | Usman Khan
6200
| Enter another feature As a user, I want to ensure my phone is durable so that I can use it for a long period. | Task 1 Research industry standard materials and build processes | 500 | Lina Dbagh
|  | Task 2 Create several prototypes with different materials and build methods | 2500 | Mansi Mistry
|  | Task 3 Test prototypes in real world situations such as drop tests and water exposure tests | 2000 | Puneet Shokar
|  | Task 4 Decide on a final design based on performance of prototypes | 800 | Usman Khan
|  | Total | 5800
| Enter another feature As a user, I want to be able to able to use a GPS application, so I can get directions to find my way to destinations. | Task 1 Create application that loads map data and allows users to search locations | 1500 | Lina Dbagh
|  | Task 2 Create algorithm that can map the route between two different addresses | 700 | Mansi Mistry
|  | Task 3 Use GPS attena to track real world location and use that location to progress current route | 1300 | Puneet Shokar
|  | Task 4 Connect with other instances of the app to track real time traffic to provide updated travel times for current route | 1250 | Usman Khan
|  | Total | 4750
| Enter user story here; As a user, I want to use voice assistant to operate the smartphone with voice commands. | Task 1 Implement text to speech API To convert vocal input to text | 800 | Lina Dbagh
|  | Task 2 Implement voice recognition API to only focus on user/owner's voice | 1000 | Mansi Mistry
|  | Task 3 Create command API that can execute commands on phone through input from text to speech API | 2000 | Puneet Shokar
|  | Task 4 Create UI to show visualization while voice prompts occur | 1200 | Usman Khan
|  | Total | 5000
| As a user, I want to access mobile payment apps, so that I can make purchases and transactions without a physical card. | Task 1 Create software to interface with NFC chip in device | 1670 | Lina Dbagh
|  | Task 2 Encrypt access to NFC chip based on user authentication | 1560 | Mansi Mistry
|  | Task 3 Connect with banking services to provide secondary authentication | 1780 | Puneet Shokar
|  | Task 4 Create application to allow users to manage payment options | 1400 | Usman Khan
|  | Total | 6410
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0

## Group Members
Mansi Mistry | mmistr32@uwo.ca
Lina Dbagh | ldbagh@uwo.ca
Usman Khan | ukhan55@uwo.ca
Puneet Shokar | pshokar2@uwo.ca