## Descriptions
Descriptions
Column Name | Possible Values | Description
Risk ID # | Incremental numbers starting with 001 | Unique identifier that all parties can refer to and know they are talking about the same issue. Will be used in team meetings to refer to a line item.
Risk Category | 1-5 Word Title | Brief explanation of the issue
Risk Description | Description | Summary of the description
WBS | WBS Number | Work breakdown structure number identified as containing a possible risk.
Activity Title | Schedule Task | The title of the activity (work breakdown structure).
Probability(%) | 2 Low 5 Medium 7 High 10 Absolute | Likelihood (percentage) the risk will occur over the identified time frame. This is critical to help determine the level of risk.
Impact Level | 1 - negligible 2 - marginal 3 - significant 4 - critical 5 - catastrophic | The impact the risk will have on the project if the risk occur. Noting whether something is High, Medium or a Low risk is a helpful field to skim down when looking for the more critical risks. The level should be determined by the impact, as well as the probability of occurrence.
Exposure | Probability * Impact Level | This will determine the exposure (severity) to the risk and will be used to rank the risks with the highest value being the highest exposure.
Impact Description | Description | Important to note why this is considered a risk and what could be impacted if the risk occurred.
Date Identified | Date Value | Date that the risk identified assists in historical data tracking for reference.
Risk Owner | Team Member | Important to know who is the owner of the risk; therefore if the issue arises there is someone who will take on the responsibility of working out the problem.
Risk Response |  | Critical to note what the plans are for each risk in case it occurs. A response could be avoidance, transference, mitigation and acceptance.
Note on A13: The impact the risk will have on the project if the risk occur. Impact is rated as • 1 - negligible • 2 - marginal • 3 - significant • 4 - critical • 5 - catastrophic
Note on A18: Risk Response: • Acceptance • Avoidance • Mitigation Transfer

## Stakeholders
| Stakeholder Name | Organization
A | Western Student Council | Western University
B | Western Campus Security | Western University
C | Students | Western University
D | Professors | Western University
E | Western Gazette | Western University
F | London Community | City of London
G | Food Vendor | Pizza Pizza
H | London Police | City of London
I | Sponsors/Investors | London Music Hall
J | Parents/Friends | Western University
K | The River Birds Band | Management Agency
L | The Ghost Dummies Band | Management Agency
M | Stage and Equipment Team | Western University
N | Sound and Light Team | Western University
O | Waste Management/Garbage Collection | London Waste Management Services
P | Beer Tent | Western University
Q | Band T-shirt Vendor | Hot Topic
R | Event Clean Up Service | Western University
S | Emegency Medical Team | Middlesex-London Health Unit
T | Western Hospitality Services | Western University
T
A
B
C
D
E
F
G
I
J
I
K
L
M
N
O
P
Q
R
S
T

## Risks Managment Plan
| Risk Management Plan | [8 empty] | 23
1 - 10 (10 = high)
ID # | Risk Category | Risk Description | WBS | Activity Title | Probability | Impact | Exposure | Impact Description and Trigger | Date Identified | Risk Owner | Risk Response
1 | Scope/Rqmt's | As a result of a lack of clear direction for the scope of work for the S/W system there could be rework which could delay the project by two to four weeks | 4.2.5 |  | 5 | 4 | 20 | Impact: Potential impact to budget and schedule. Trigger: Team finds unclear or no suitable requirement(s) to meet a work package | 2014-05-14 | First and last name | Mitigate: pull project team, BA and customer to define needed requirements
2 | Lack of performers | As a result of the bands being known for overindulging themselves and having issues with crossing borders, the performance may be late or cancelled, which could lead to profit goals not being met |  |  | 7 | 5 | 35 | Impact: Impacts to schedule and/or profits Trigger: One or both bands cannot arrive on time | 2023-05-14 |  | Mitigate: Have backup performers available and contingency plans in place
3 | Damage to Venue | As a result result of excessive attendance during the concert, garbage and littering can cause excessive clean up costs and damage to campus grounds |  |  | 9.5 | 1 | 9.5 | Impact: Increases cleaning costs Trigger: Excessive Attendance | 2023-05-14 |  | Mitigate: Have clear signs and accessible bins to encourage proper dispsable of garbage.
4 | Technical Issues | As a result of equiment malfunction or failure, technical issues with sound and lighting equipment can lead to poor performance quality and lack of satisfaction from fans |  |  | 4 | 4 | 16 | Impact: Impacts to overall satisfaction of fans Trigger: Technical difficulties during either of the performances | 2023-05-14 |  | Transfer: Have tech team administer thorough testing of all sound and lighting equipment prior to the event.
5 | Damage to Venue | As a result result of excessive attendance during the concert, vandalism can cause damage to campus grounds, resulting in additonal financial costs |  |  | 5 | 3 | 15 | Impact: Damage to venue Trigge: Damage occurs | 2023-05-14 |  | Mitigate: Limit the selling of tickets before and during the event.
6 | Technical Issues | As a result of the event being held outdoors, there could be unpredictable weather conditions leading to damage of event equipment. |  |  | 4 | 4 | 16 | Impact: Delay /or cancels show, loss of revenue Trigger: Bad unpredictable weather | 2023-05-14 |  | Avoid: Scheduling concert during unprobable weather conditions.
7 | Safety Issues | As a result of people sneaking in, venue capacity may be exceeded, resulting in safety risks |  |  | 5 | 3 | 15 | Impact: Increased safety risk for all attendees Trigger: Vulrenablities in venue security allowing people to sneak in | 2023-05-14 |  | Mitigate: Have strict security measures in place.
8 | Lack of vendors | As a result in food vendors backing out, attendees may become upset and demand refunds, resulting in decreased revenues |  |  | 2 | 4 | 8 | Impact: Decreased satisfaction of attendees, loss of revenue Trigger: Once one or more vendors cancel without enough notice | 2023-05-14 |  | Mitigate: Have backup food vendors and offer alternative compensation for attendees
9 | Damage to Venue | As a result of a large crowd and the involvement of alcohol, potential conflicts can cause security issues with crowd control and safety, which can lead to injury and damage to the University's reputation |  |  | 5 | 3 | 15 | Impact: Increased safety risk for all attendees Trigger: Exessive partying, alcohol consumption. | 2023-05-14 |  | Mitigate: Ensure proper security for the venue and pose a maximum limit for attendees.
10 | Theft | As a result of large crowds and insufficient security, theft of T-shirt vendor merchandice may occur which can result in loss of profit |  |  | 4 | 3 | 12 | Impact: Loss of revenue, loss of trust between vendor and school Trigger: Theft Occurs | 2023-05-14 |  | Mitigate: Have security available on all corners of the event and a help desk area.
11 | Logistical Issues | As a result of the stage team not being able to set the venue up in time, the event could be delayed, resulting in scheduling conflicts |  |  | 2 | 4 | 8 | Impact: Scheduling issues, delayed event Trigger: Venue not setup on time | 2023-05-14 |  | Mitigate: Ensure to plan ahead on staging and venue preperations.
12 | Damage to Venue | As a result of the university hosting a large event with the involvment of alchohol and entertainment, there could be damage to the school grounds. |  |  | 9.5 | 2 | 19 | Impact: Increased financial cost Trigger: Excessive Partying | 2023-05-14 |  | Accept: This is a necessary risk for a large scale event
13 | University Reputation | As a result of the event being available to the London public, potential children attending the event could get lost, resulting in safety issues. |  |  | 4 | 3 | 12 | Impact: the safety of children attending Trigger: guardians failing to watch children | 2023-05-14 |  | Mitigate the risk: Require young children to remain with a parent or guardian
14 | Technical Issues | As a result of a power outage, the performers may not be able to put on the show, resulting in attendess requesting refunds |  |  | 1 | 5 | 5 | Impact: Impacts to schedule and/or profits Trigger: One or both bands cannot perform due to lack of power | 2023-05-14 |  | Mitigate: Have backup generators and contingency plan
15 | Logistical Issues | As a result of ticket sales possibly not being met, estimated profit margins won't be met causing a loss for the University |  |  | 4 | 4 | 16 | Impact: Impacts to profits Trigger: Not enough promotion by organizers. | 2023-05-14 |  | Mitigate: Have a ticket presale to ensure meeting ticket sale goals.
16 | Safety Issues | As a result to there being food and alcohol vendors, there can be food and health safety hazards such as food and alcohol poisoning. |  |  | 5 | 3 | 15 | Impact: Health risks to attendees consuming food and/or drink Trigger: Complaints of improperly cooked food | 2023-05-14 |  | Avoid: Ensure that all food vendors follow food safety regulations and take proper health and safety measures
17 | University Reputation | As a result of loud music and noise from the concert, local neighbours may submit noise complaints, which can result in a negative impact on the relationship between the London Community and the University |  |  | 3 | 3 | 9 | Impact: Fines from City, negative impact in cities perception of the school Trigger: Poor planning and lack of permits prior to event | 2023-05-14 |  | Avoid: Provide local community with adequate notice prior to the event and encourage attendance
18 | Safety Issues | As a result of high event attendance and crowding, insufficient medical and first-aid services can cause potential for higher injury rates and overwhelming of medical staff |  |  | 4 | 3 | 12 | Impact: Safety risks to attendees Trigger: When/if medical staff gets overwhelmed | 2023-05-14 |  | Mitigate: increase the number of medical and first-aid services available.
19 | Safety Issues | As a result of outdoor food vendors, fire hazards could occur with the use of open flames and/or grills with the addition of direct sunlight. |  |  | 4 | 3 | 12 | Impact: Impacts to safety of attendants. Trigger: Food vendors not following health precautions. | 2023-05-14 |  | Avoid: Ensure that all outdoor food vendors prevent direct exposure to sunlight and follow fire safety regulations
20 | Safety Issues | As a result of there being an older audience and the show taking place on university grounds there could be a breach of drug use or drugs brought into the premisis posing health and safety risks. |  |  | 5 | 3 | 15 | Impact: Impacts to health and safety of attendees. Trigger: Reckless behaviour by some audience or organization members. | 2023-05-14 |  | Avoid: Ensure security measures prevent any drug use or attandents under the influence from entering
Note on B5: Risk Categories are a common listing of sources of risk. Depending on the size of the project, one might employ a Risk Breakdown Structure (RBS). I.e. Infrastructure, S/W, financial, people
Note on C5: Description of the risk
Note on D5: WBS number
Note on F5: Likelihood(percentage) the risk will occur over the identified time frame.(25% low, 50% medium, 75% high, 100% absolute)
Note on G5: The impact the risk will have on the project if the risk occur. Impact is rated as • 1 - negligible • 2 - marginal • 3 - significant • 4 - critical • 5 - catastrophic
Note on L5: Risk Response: Acceptance Avoidance Mitigation Transfer And a corrective plan
Note on C6: Mckenna, David: As a result of (definitive cause), (uncertain event) may occur, which could lead to (effect)

## Cause risk effect
Cause: | Risk: | Effect:

## Risk Summary
Risk Summary
Project Name:
Project Manager: |  | David McKenna
Rank | ID # | Title | Status | Exposure | Risk Owner | Risk Response
1 | 1 |  | 4.2.5 | 20 | First and last name | Mitigate: pull project team, BA and customer to define needed requirements
2 | 2 |  | 0 | 35 | 0 | Mitigate: Have backup performers available and contingency plans in place
3 | 3 |  | 0 | 9.5 | 0 | Mitigate: Have clear signs and accessible bins to encourage proper dispsable of garbage.
4 | 4 |  | 0 | 16 | 0 | Transfer: Have tech team administer thorough testing of all sound and lighting equipment prior to the event.
5 | 5 |  | 0 | 15 | 0 | Mitigate: Limit the selling of tickets before and during the event.
6 | 6 |  | 0 | 16 | 0 | Avoid: Scheduling concert during unprobable weather conditions.
7 | 7 |  | 0 | 15 | 0 | Mitigate: Have strict security measures in place.
8 | 8 |  | 0 | 8 | 0 | Mitigate: Have backup food vendors and offer alternative compensation for attendees
9 | 9 |  | 0 | 15 | 0 | Mitigate: Ensure proper security for the venue and pose a maximum limit for attendees.
10 | 10 |  | 0 | 12 | 0 | Mitigate: Have security available on all corners of the event and a help desk area.
11 | 11 |  | 0 | 8 | 0 | Mitigate: Ensure to plan ahead on staging and venue preperations.
12 | 12 |  | 0 | 19 | 0 | Accept: This is a necessary risk for a large scale event
13 | 13 |  | 0 | 12 | 0 | Mitigate the risk: Require young children to remain with a parent or guardian
14 | 14 |  | 0 | 5 | 0 | Mitigate: Have backup generators and contingency plan
15 | 15 |  | 0 | 16 | 0 | Mitigate: Have a ticket presale to ensure meeting ticket sale goals.
16 | 16 |  | 0 | 15 | 0 | Avoid: Ensure that all food vendors follow food safety regulations and take proper health and safety measures
17 | 17 |  | 0 | 9 | 0 | Avoid: Provide local community with adequate notice prior to the event and encourage attendance
18 | 18 |  | 0 | 12 | 0 | Mitigate: increase the number of medical and first-aid services available.
19 | 19 |  | 0 | 12 | 0 | Avoid: Ensure that all outdoor food vendors prevent direct exposure to sunlight and follow fire safety regulations
20 | 20 |  | 0 | 15 | 0 | Avoid: Ensure security measures prevent any drug use or attandents under the influence from entering
Note on E7: Sort by descending